## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-02-19 | Done | Max 4 hours tasks | What is fairness? | Study | ILO 4.1: Responsible AI | 2 | 2 | 0
2024-02-19 | Done | Max 4 hours tasks | The Difference Between Equality and Equity | Study | ILO 4.1: Responsible AI | 3 | 3 | 0
2024-02-19 | Done | Max 4 hours tasks | The Difference Between Explicit and Implicit Bias | Study | ILO 4.1: Responsible AI | 3 | 3 | 0
2024-02-19 | Done | Max 4 hours tasks | Review with peer | Meeting | ILO 1.3: Professional Practice | 1 | 1 | 0 |  | We reviewed our question 3a and 3b with a colleague.
2024-02-19 | Done | Max 4 hours tasks | Submitting the quiz | Study | ILO 4.1: Responsible AI | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_summary.d2l?qi=1078&ou=8760
2024-02-20 | Done | Max 4 hours tasks | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-02-20 | Done | Max 4 hours tasks | Evidencing worklog | Evidencing | ILO 1.3: Professional Practice | 0.75 | 0.75 | 0
2024-02-20 | Done | Max 4 hours tasks | Kick-Off Presentation | Lecture | ILO 1.3: Professional Practice | 2 | 2 | 0
2024-02-20 | Done | Max 4 hours tasks | DataLab Task | Study | ILO 3.1: Business Understanding | 3.5 | 3.5 | 0 |  | My final dataset is on wheat to predict when is ready to be harvested or not.
2024-02-21 | Done | Max 4 hours tasks | Bias & Machine Learning | Study | ILO 3.1: Business Understanding | 2 | 2 | 0
2024-02-21 | Done | Max 4 hours tasks | Individual Fairness, and Debiasing Techniques | Study | ILO 4.1: Responsible AI | 2 | 2 | 0
2024-02-21 | Done | Max 4 hours tasks | Group fairness Metrics | Study | ILO 4.1: Responsible AI | 4 | 4 | 0
2024-02-21 | Done | Max 4 hours tasks | Submitting the quiz | Study | ILO 4.1: Responsible AI | 0.5 | 0.5 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_summary.d2l?qi=1079&ou=8760
2024-02-22 | Done | Max 4 hours tasks | Market Research and Stakeholders | Study | ILO 3.1: Business Understanding | 1 | 1 | 0
2024-02-22 | Done | Max 4 hours tasks | DAPS Diagram | Study | ILO 3.1: Business Understanding | 2 | 2 | 0
2024-02-22 | Done | Max 4 hours tasks | Market research, problem identification & stakeholder analysis | Study | ILO 3.1: Business Understanding | 4 | 4 | 0
2024-02-23 | Done | Max 4 hours tasks | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-02-23 | Done | Max 4 hours tasks | DataLab Task Idea Generation | Study | ILO 3.1: Business Understanding | 3.5 | 3.5 | 0
2024-02-23 | Done | Max 4 hours tasks | Created my final dataset |  |  | 4 | 4 | 0 | Dataset_Block_C | My final idea is to Predict which flower is the camera points.
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 40.25 | 40.25 | 0
Week 2
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-02-26 | Done | Max 4 hours tasks | Set up a Development Environment for Deep Learning | Programming | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-02-26 | Done | Max 4 hours tasks | Introduction to Deep Learning data camp cousre | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-02-26 | Done | Max 4 hours tasks | Quiz 16 questions | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-02-26 | Done | Max 4 hours tasks | Deep Learning book first two chapters | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-02-27 | Done | Max 4 hours tasks | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-02-27 | Done | Max 4 hours tasks | Reading Today's Material about Preprocessing Image Data | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-02-27 | Done | Max 4 hours tasks | Practical Assignment (Regression and Binary Classification Tasks) | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-02-27 | Done | Max 4 hours tasks | Practical Assignment Multi-class Classification | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-02-27 | Done | Max 4 hours tasks | Review session assessment Block B | Meeting | ILO 1.3: Professional Practice | 2 | 2 | 0
2024-02-28 | Done | Max 4 hours tasks | TensorFlow and Keras | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-02-28 | Done | Max 4 hours tasks | Fundamental Machine Learning Concepts | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-02-28 | Done | Max 4 hours tasks | Quiz submission | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-02-28 | Done | Max 4 hours tasks | Data Lab tasks idea | Study | ILO 4.1: Responsible AI | 2 | 2 | 0
2024-02-29 | Done | Max 4 hours tasks | Introduction to Model Evaluation | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-02-29 | Done | Max 4 hours tasks | Training, Validation and Test Sets | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-02-29 | Done | Max 4 hours tasks | Improving Your Model Performance | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-02-29 | Done | Max 4 hours tasks | Quiz submission | Study | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_summary.d2l?qi=1175&ou=8760
2024-03-01 | Done | Max 4 hours tasks | Q&A and Standup | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-01 | Done | Max 4 hours tasks | Reading Today's Material and Tasks | Study | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.25 | -0.25
2024-03-01 | Done | Max 4 hours tasks | Practical Assignment (Learning Curves) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-01 | Done | Max 4 hours tasks | Practical Assignment (Early Stopping) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-01 | Done | Max 4 hours tasks | Practical Assignment (Tuning learning rate) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-01 | Done | Max 4 hours tasks | Review Sesion | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
|  |  |  | Total Hours |  | 35.5 | 35.25 | -0.25
Week 3
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-03-04 | Done | Data lab Preapartation | Understanding Neural Networks(Stat Quest) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-04 | Done | Data lab Preapartation | Key concepts of Neurons | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-04 | Done | Data lab Preapartation | Submitting the quiz | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?isprv=0&fromQB=0&qi=1176&cfql=0&ou=8760
2024-03-04 | Done | Data lab Preapartation | Calculating the Output of a Multilayer Perceptron | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-03-05 | Done | Data lab | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0 | MLP from scratch
2024-03-05 | Done | Data lab | Reading today's assignment and structure of the Jupyter notebook | Study | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 1 | 0.5 |  | There was more material than the expected.
2024-03-05 | Done | Data lab | Practical Assignment (Task 1: Build an MLP) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-05 | Done | Data lab | Practical Assignment (Task 2: Sigmoid Activation Function) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-05 | Done | Data lab | Practical Assignment (Task 3: Predict Function) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-05 | Done | Data lab | Practical Assignment (Task 4: Calculate Accuracy) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 2 | 1
2024-03-05 | Done | Data lab | Practical Assignment (Task 5: Loss Function) | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-06 | Done | Data lab Preapartation | Overview of the Machine Learning Project Lifecycle | Study | ILO 5.1: Neural Networks and Deep Learning | 4 | 4 | 0
2024-03-06 | Done | Data lab Preapartation | Exploring the Phases of the Machine Learning Project Lifecycle | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-03-06 | Done | Data lab Preapartation | Quiz submission | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?isprv=0&fromQB=0&qi=1177&cfql=0&ou=8760
2024-03-07 | Done | Data lab Preapartation | Gradient Descent in Neural Networks | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0 | Gradient Descent
2024-03-07 | Done | Data lab Preapartation | Naive Gradient Descent Implementation | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-07 | Done | Data lab Preapartation | Quiz submission | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?qi=1178&ou=8760
2024-03-07 | Done | Data lab Preapartation | chapter 6 of the book Deep Learning with Python. | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-08 | Done | Data lab | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-08 | Done | Data lab | Reading today's assignment and introduction to the gradient descent algorithm | Study | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5 | 0
2024-03-08 | Done | Data lab | Making a Form for the project | Research | ILO 3.1: Business Understanding | 3 | 3 |  | https://docs.google.com/forms/d/1R2WTAaZZ_xfxYOfOYzAv78qVxvXEq5VHvO287ETQaDs/edit
2024-03-08 | Done | Data lab | Practical Assignment (Task 6.1: Update a Single Weight) | Programming | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5 |  | MLP from scratch
2024-03-08 | Done | Data lab | Practical Assignment (Task 6.2: Update a Single Bias) | Programming | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5
2024-03-08 | Done | Data lab | Practical Assignment (Task 6.3: Estimate the Partial Derivatives) | Programming | ILO 5.1: Neural Networks and Deep Learning | 1 | 1
2024-03-08 | Done | Data lab | Practical Assignment (Task 6.4: One-Step Gradient Descent) | Programming | ILO 5.1: Neural Networks and Deep Learning | 1 | 1
2024-03-08 | Done | Data lab | Practical Assignment (Task 6.5: Repeat the One-Step Gradient Descent) | Programming | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5
2024-03-08 | Done | Data lab | Week 9-10 Challenges | Meeting | ILO 1.3: Professional Practice | 0.25 | 0.25
2024-03-08 | Done | Data lab | Guest Lecture | Meeting | ILO 1.3: Professional Practice | 1 | 1 | 0
|  |  |  | Total Hours |  | 37.75 | 39.25 | 1.5
Week 4
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-03-11 | Done | Data lab preparation | Understanding Convolutions | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/Week_4/DataLab_Prepration_I.ipynb
2024-03-11 | Done | Data lab preparation | Image Modeling with Keras | Programming | ILO 5.1: Neural Networks and Deep Learning | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/Image%20modeling%20with%20Keras.pdf
2024-03-11 | Done | Data lab Preapration | Quiz submission | Study | ILO 1.3: Professional Practice | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?qi=1179&ou=8760
2024-03-12 | Done | Data lab | Stand up | Study | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-12 | Done | Data lab | Reading today's task | Study | ILO 2.2: Personal Development & Academic Practice | 0.5 | 0.5 | 0
2024-03-12 | Done | Data lab | DataLab Task 3.2 (Preprocessing) | Study | ILO 1.3: Professional Practice | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-12 | Done | Data lab | DataLab Task 3.3 (CNN Architecture) | Study | ILO 1.3: Professional Practice | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-12 | Done | Data lab | DataLab Task 3.4 (CNN Training | Study | ILO 1.3: Professional Practice | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-12 | Done | Data lab | DataLab Task 3.5 (Model Performance) | Study | ILO 1.3: Professional Practice | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-13 | Done | Data lab preparation | Convolutional Neural Networks | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-03-13 | Done | Data lab preparation | Error Analysis | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/08f88fc9ede6940c3cab42163d3706168789e3c3/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-13 | Done | Data lab preaparation | Quiz submission | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?isprv=0&fromQB=0&qi=1180&cfql=0&ou=8760
2024-03-14 | Done | Data lab preapration | Collecting More Data | Study | ILO 5.1: Neural Networks and Deep Learning | 1 | 1 | 0
2024-03-14 | Done | Data lab Preaparation | Data Augmentation | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/Week_4/DataLab%20Preparation%20(Week%204%2C%20DataLab%20II%2C%20Thursday).ipynb
2024-03-14 | Done | Data lab Preaparation | Transfer Learning | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-14 | Done | Data lab Preaparation | Quiz submission | Study | ILO 1.3: Professional Practice | 1 | 1 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?qi=1181&ou=8760
2024-03-15 | Done | Data lab Task | Q&A and Standup | Study | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-15 | Done | Data lab Task | Reading today's tasks | Study | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-15 | Cancelled | Data lab Task | DataLab Tasks (Apply Data Augmentation) | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 0 | -3 |  | Have not started them yet I allocated more hours my next week for this tasks
2024-03-15 | Cancelled | Data lab task | DataLab Tasks (Apply Transfer Learning) | Study | ILO 5.1: Neural Networks and Deep Learning | 3 | 0 | -3
2024-03-15 | Done | Data lab | Filling work log and learning log | Study | ILO 1.3: Professional Practice | 2 | 2 | 0
2024-03-15 | Done | Data lab | Review session |  |  | 0.5 | 0.5 | 0
|  |  |  | Total Hours |  | 38.5 | 32.5 | -6
Week 5
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-03-18 | Done | Data lab preparation | Overview of the Machine Learning Project Lifecycle | Study | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5 | 0
2024-03-18 | Done | Data lab preparation | Introduction to Machine Learning in Production | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-18 | Done | Data lab preparation | Deployment | Programming | ILO 5.1: Neural Networks and Deep Learning | 0.5 | 0.5 | 0
2024-03-18 | Done | Data lab preparation | Selecting and Training a Model | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-18 | Done | Data lab preparation | Human-Level Performance (HLP) | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0 |  | Got 15 responses
2024-03-19 | Done | Data lab | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-19 | Done | Data lab | DataLab Task 3.1: Baselines | Programming | ILO 5.1: Neural Networks and Deep Learning | 2.5 | 2.5 | 0
2024-03-19 | Done | Data lab | DataLab Task 3.6: Error Analysis | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-19 | Done | Data lab | Improving Your Model | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-20 | Done | Data lab preparation | Error Analysis and Performance Auditing | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-20 | Done | Data lab preparation | Data Iteration | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-20 | Done | Data lab preparation | DataLab Tasks | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-03-21 | Done | Data lab preparation | Define Data and Establish Baseline | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-03-21 | Done | Data lab preparation | Label and Organize Data | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-21 | Done | Data lab preparation | Scoping | Study | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-21 | Done | Data lab preparation | DataLab Tasks (Apply Data Augmentation) | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 4 | 1 |  | Had problem with the code it was
2024-03-22 | Done | Data lab | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-22 | Done | Data lab | Data lab task iteration 1 | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 4 | 1 |  | It was more time than the expected the reason being that I had a problem with loading my data and Borislav helped me
2024-03-22 | Done | Data lab | Data lab task iteration 2 | Programming | ILO 5.1: Neural Networks and Deep Learning | 2 | 2 | 0
2024-03-22 | Done | Data lab | Preparation of the Project Presentation | Planning | ILO 6.1 Human-Centered AI | 2 | 2 | 0
2024-03-22 | [7 empty] | 0
|  |  |  | Total Hours |  | 38.5 | 40.5 | 2
Week 6
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-03-25 | Done | Data lab preparation | What is XAI and Why is it Important? | Study | ILO 4.1: Responsible AI | 2 | 2 | 0
2024-03-25 | Done | Data lab preparation | Use Case: Healthcare for XAI | Study | ILO 4.1: Responsible AI | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-25 | Done | Data lab preparation | Taxonomy of XAI | Study | ILO 4.1: Responsible AI | 1 | 1 | 0
2024-03-25 | Done | Data lab preparation | What is a ‘Good' Explanation? | Study | ILO 4.1: Responsible AI | 3 | 3 | 0
2024-03-25 | Done | Data lab preparation | A Provocative Perspective: ‘Do we Really want Explainable AI? | Study | ILO 4.1: Responsible AI | 1.5 | 1.5 | 0
2024-03-25 | Done | Data lab preparation | Quiz submission | Study | ILO 1.3: Professional Practice | 1 | 1 | 0 |  | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?qi=1225&ou=8760
2024-03-26 | Done | Data lab | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-03-26 | Done | Data lab | Presentation on XAI: Preparation | Design | ILO 1.3: Professional Practice | 2.5 | 2.5 | 0
2024-03-26 | Done | Data lab | Presentation: Presenting | Meeting | ILO 1.3: Professional Practice | 2.5 | 2.5 | 0
2024-03-26 | Cancelled | Data lab | Data lab task Taxomony of AI |  |  | 1.5 |  | -1.5 |  | Allocated another tim e for this task in the upcomming week
2024-03-26 | Done | Final Deliverable | Iteration 4 Transfer Learning | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 3 | 0
2024-03-27 | Done | Data lab preparation | Pixel Attribution: Vanilla Gradients | Programming | ILO 4.1: Responsible AI | 2 | 2 | 0
2024-03-27 | Done | Data lab preparation | Integrated Gradients | Programming | ILO 4.1: Responsible AI | 1.5 | 1.5 | 0
2024-03-27 | Done | Data lab preparation | Grad-CAM | Programming | ILO 4.1: Responsible AI | 2.5 | 2.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-03-27 | Done | Data lab preparation | Quiz submission | Study | ILO 1.3: Professional Practice | 1 | 1 | 0
2024-03-28 | Done | Data lab preparation | Pixel Attribution: Lime | Programming | ILO 4.1: Responsible AI | 2 | 2 | 0
2024-03-28 | Done | Data lab preparation | SHAP | Programming | ILO 4.1: Responsible AI | 1.5 | 1.5 | 0
2024-03-28 | Done | Data lab preparation | Adversarial Attacks & Counterfactuals | Programming | ILO 4.1: Responsible AI | 1.5 | 1.5 | 0
2024-03-28 | Done | Final Deliverable | DataLab: Catch-Up Time(Error Analysis) | Programming | ILO 5.1: Neural Networks and Deep Learning | 3 | 3
2024-03-28 | Done | Data lab Preparation | Quiz submission | Study | ILO 1.3: Professional Practice | 1 | 1
0
|  |  |  | Total Hours |  | 35 | 33.5 | -1.5
Week 7
Known Risks | It does not reach 32 hours because it was 4 working days
2024-04-02 | Done | Max 4 hours tasks | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-04-02 | Done | Max 4 hours tasks | Review Sesion | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-04-02 | Done | Max 4 hours tasks | Learning log and working log | Study | ILO 1.3: Professional Practice | 3 | 3 | 0
2024-04-03 | Done | Data lab preparation | Learning about Human-Centered AI | Study | ILO 6.1 Human-Centered AI | 1 | 1 | 0
2024-04-03 | Done | Data lab preparation | Interaction and Information Processing Fundamentals | Study | ILO 6.1 Human-Centered AI | 1 | 1 | 0
2024-04-03 | Done | Data lab preparation | Design Thinking | Workshop | ILO 6.1 Human-Centered AI | 1 | 1.2 | 0.2 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/CertificateOfCompletion_Design%20Thinking%20Understanding%20the%20Process.pdf | This is the certificate for Design Thinking, It took some time to complete.
2024-04-03 | Done | Data lab preparation | Flow theory | Workshop | ILO 6.1 Human-Centered AI | 1 | 0.8 | -0.2 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/CertificateOfCompletion_Interaction%20Design%20Flow.pdf | This is the certificate for flow theory, It took less time than the expected.
2024-04-03 | Done | Data lab preparation | DataLab Preparation(Quiz submission) | Study | ILO 1.3: Professional Practice | 3 | 3 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?qi=1231&ou=8760 | Quiz submission
2024-04-04 | Done | Data lab preparation | Interaction design (Linkedin course) | Workshop | ILO 1.3: Professional Practice | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/CertificateOfCompletion_UX%20Foundations%20Interaction%20Design.pdf
2024-04-04 | Done | Data lab Preparation | Interface design (Linkedin course) | Workshop | ILO 6.1 Human-Centered AI | 1 | 0.7 | -0.3 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/CertificateOfCompletion_Interaction%20Design%20Interface%20.pdf
2024-04-04 | Done | Data lab Preparation | Introduction to Figma | Study | ILO 6.1 Human-Centered AI | 2 | 2 | 0
2024-04-05 | Done | Data lab | Stand up | Meeting | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-04-05 | Done | Data lab | Read the material on think-aloud studies | Study | ILO 6.1 Human-Centered AI | 0.5 | 0.5 | 0
2024-04-05 | Cancelled | Data lab | Prepare (paper) prototype | Testing | ILO 6.1 Human-Centered AI | 2 | 0 | -2 |  | I started immediatley on my Figma design Already had a plan in mind
2024-04-05 | Done | Data lab | Prepare prototype (Figma) | Testing | ILO 6.1 Human-Centered AI | 2 | 2 | 0
2024-04-05 | Done | Data lab | Execute study and participate in the study(Think aloud study) | Testing | ILO 6.1 Human-Centered AI | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Task%204.1%20Think_Aloud_Study/Think_aloud_study_feedback.txt
2024-04-05 | Done | Data lab | Analyze the results | Study | ILO 6.1 Human-Centered AI | 2 | 2 | 0 | https://study.buas.nl/d2l/lms/quizzing/user/quiz_submissions.d2l?isprv=0&fromQB=0&qi=1084&cfql=0&ou=8760
|  |  |  | Total Hours |  | 27 | 24.7 | -2.3
Week 8
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-04-08 | Cancelled | Datal lab Preparation | LinkedIn course on user testing | Study | ILO 6.1 Human-Centered AI | 1.5 |  | -1.5
2024-04-08 | Done | Datal lab Preparation | Background on A/B testing | Study | ILO 6.1 Human-Centered AI | 0.5 | 0.5 | 0
2024-04-08 | Done | Datal lab Preparation | Datacamp course on A/B testing | Study | ILO 6.1 Human-Centered AI | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/CertificateOfCompletion_UX%20Foundations%20Usability%20Testing.pdf
2024-04-08 | Done | Datal lab Preparation | Preparing for A/B testing in DataLab | Design | ILO 6.1 Human-Centered AI | 3 | 3 | 0
2024-04-09 | Done | Data lab | Evidencing Learning Log and Learning Log | Study | ILO 1.3: Professional Practice | 2 | 2 | 0
2024-04-09 | Done | Data lab | stand up | Study | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-04-09 | Done | Data lab | A/B Testing in rounds | Study | ILO 6.1 Human-Centered AI | 5 | 5 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/AB_test/A_B_Test_B.xlsx
2024-04-09 | Done | Data lab | Analyze results | Workshop | ILO 6.1 Human-Centered AI | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/AB_test/T-testIndependentSamplesHCAI.ipynb
2024-04-10 | Done | Final Deliverable | Creating the demo video for your wireframe: | Study | ILO 6.1 Human-Centered AI | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Video%20for%20the%20wireframe/Untitled%20video%20-%20Made%20with%20Clipchamp.mp4
2024-04-10 | Done | Final Deliverable | Presentation on XAI: Preparation | Study | NA | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/Final_deliverables/Project-Presentation.pptx
2024-04-11 | Done | Final Deliverable | Fixing my Iteration 3 | Study | ILO 5.1: Neural Networks and Deep Learning | 5 | 5 | 0
2024-04-11 | Done | Final Deliverable | Making a new kernel | Study | ILO 4.1: Responsible AI | 3 | 3 | 0 |  | My last kernel did not use the Gpu and the code ran for a long time made a new one
2024-04-11 | Done | Final Deliverable | Trying to fix my grid cam | Study | ILO 4.1: Responsible AI | 4 | 4 | 0 |  | Did not fix it
2024-04-12 | Done | Final Deliverable | Stand up | Study | ILO 1.3: Professional Practice | 0.5 | 0.5 | 0
2024-04-12 | Done | Final Deliverable | Mlp from Scratch | Programming | ILO 6.1 Human-Centered AI | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/main/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-04-12 | Done | Final Deliverable | Presentation on XAI: Preparation | Meeting | ILO 1.3: Professional Practice | 3 | 3 | 0
2024-04-12 | Done | Final Deliverable | Evidencing | Study | ILO 1.3: Professional Practice | 2 | 2 | 0
|  |  |  | Total Hours |  | 43 | 41.5 | -1.5
|  |  |  | Total Hours in this Block |  | 295.5 | 287.45 | -8.05

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.3: Professional Practice | W1: 0 | 0
ILO 2.2: Personal Development & Academic Practice | [8 empty] | 0
ILO 3.1: Business Understanding | [8 empty] | 0
ILO 4.1: Responsible AI | [8 empty] | 0
ILO 5.1: Neural Networks and Deep Learning | [8 empty] | 0
ILO 6.1 Human-Centered AI | [8 empty] | 0
NA | [8 empty] | 0
NA | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.3: Professional Practice
Unplanned | Meeting | ILO 2.2: Personal Development & Academic Practice | Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!
Blocked | Programming | ILO 3.1: Business Understanding
In-Progress | Research | ILO 4.1: Responsible AI
Done | Testing | ILO 5.1: Neural Networks and Deep Learning
Delayed | Workshop | ILO 6.1 Human-Centered AI
Cancelled | Planning | NA
| Evidencing | NA
Debugging
Lecture
Study
Unplanned
Distraction
Break